10.3 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 韌體設計 | 張政崙 | 2025-02-07 | #VALUE! | #VALUE! | 2025-02-14 |  |  | Complete | 0 | 2025/01/20 | 45677%
10.4 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 機構開模 | 葉宏政 | 2025-05-28 | #VALUE! | #VALUE! | 2025-02-05 |  |  | Complete | 0 | 2024/10/28 | 45678%
10.5 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | PCB送洗(2塊) | 黃胤綸 | 2025-01-23 | #VALUE! | #VALUE! | 2025-02-05 |  |  | Complete | 0 | 2025/01/15 | 45679%
10.6 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 機構審查 | 鄭貫中 | 2025-02-04 | #VALUE! | #VALUE! | 2025-02-13 |  |  | Complete | 0 | 2025/01/13 | 45679%
10.7 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 機構樣品製作 | 鄭貫中 | 2025-02-04 | #VALUE! | #VALUE! | 2025-04-11 |  |  | Complete | 0 | 2025/01/22 | 45679%
10.8 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | PVT-QA測試驗證 | 陳威宏 | 2025-03-12 | #VALUE! | #VALUE! | 2025-03-05 |  |  | Complete | 0 | 2025/01/23 | 45679%
10.9 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 電路板焊接(2塊各5 PCS) | 李騏敬 | 2025-02-03 | #VALUE! | #VALUE! | 2025-02-08 |  |  | Complete | 0 | 2025/01/20 | 45681%
11 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 治具配線與功能驗證 | 魏暉恩 | 2025-02-07 | #VALUE! | #VALUE! | 2025-05-06 |  |  | Complete | 0 | 2025/04/21 | 45691%
11.1 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 硬體電路功能測試(PT1000與RS485) | 李騏敬 | 2025-02-10 | #VALUE! | #VALUE! | 2025-02-08 |  |  | Complete | 0 | 2025/01/23 | 45692%
11.2 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 機構圖面修改 | 鄭貫中 | 2025-02-11 | #VALUE! | #VALUE! | 2025-03-17 |  |  | Complete | 0 | 2025/02/27 | 45693%
11.3 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 整合功能驗證(硬體/韌體/機構整合) | 李騏敬 | 2025-02-11 | #VALUE! | #VALUE! | 2025-02-20 |  |  | Complete | 0 | 2025/02/11 | 45693%
11.4 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 工況試煉送樣 | 蘇哲弘 | 2025-04-08 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/11/27 | 45695%
11.5 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 測試治具設計及製作/移交清單 | 蘇哲弘 | 2025-02-11 | #VALUE! | #VALUE! | 2026-01-09 |  |  | Complete | 0 | 2025/11/21 | 45695%
11.6 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | QC工程表 | 蘇哲弘 | 2025-02-13 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/11/14 | 45695%
11.7 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 進料檢驗基準 | 魏暉恩 | 2025-02-13 | #VALUE! | #VALUE! | 2025-09-15 |  |  | Complete | 0 | 2025/08/25 | 45695%
11.8 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 產品檢驗基準 | 魏暉恩 | 2025-02-13 | #VALUE! | #VALUE! | 2025-09-12 |  |  | Complete | 0 | 2025/09/11 | 45695%
11.9 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 產品檢驗記錄 | 魏暉恩 | 2025-02-13 | #VALUE! | #VALUE! | 2025-09-12 |  |  | Complete | 0 | 2025/09/12 | 45695%
12 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 請廠務進行PCBA打件 (基本：A:20套 / K:50套 / M:100套，需在專案會議再次確認) | 蘇哲弘 | 2025-02-27 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/08/25 | 45695%
12.1 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | PCB 圖面 | 許慧芝 | 2025-02-13 | #VALUE! | #VALUE! | 2025-05-05 |  |  | Complete | 0 | 2025/05/05 | 45695%
12.2 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 機構圖面(元件/組裝/銘版) | 王瀚霆 | 2025-02-13 | #VALUE! | #VALUE! | 2025-06-06 |  |  | Complete | 0 | 2025/05/20 | 45695%
12.3 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 標籤貼紙 (回覆標籤版型料號) | 蘇哲弘 | 2025-02-13 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/10/29 | 45695%
12.4 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 進料檢驗基準(機構) | 王瀚霆 | 2025-02-13 | #VALUE! | #VALUE! | 2025-06-06 |  |  | Complete | 0 | 2025/05/22 | 45695%
12.5 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 韌體審查 | 張政崙 | 2025-02-11 | #VALUE! | #VALUE! | 2025-09-10 |  |  | Complete | 0 | 2025/02/12 | 45698%
12.6 | K240801R2 | PCB濕製程用插入式壓力感測器 | DVT-QA測試(含競爭樣機性能對照) | 陳威宏 | 2025-03-10 | #VALUE! | #VALUE! | 2025-06-18 |  |  | Complete | 0 | 2025/03/05 | 45698%
12.7 | K240801R2 | PCB濕製程用插入式壓力感測器 | DVT-QA樣機EOM建立 | 張良琪 | 2025-02-10 | #VALUE! | #VALUE! | 2026-01-23 |  |  | Complete | 0 | 2026/01/23 | 45698%
12.8 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 工況試煉送樣 | 黃胤綸 | 2025-02-18 | #VALUE! | #VALUE! | 2025-02-13 |  |  | Complete | 0 | 2025/02/07 | 45700%
12.9 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 模具設計與開模(本體/配件) | 鄭貫中 | 2025-03-19 | #VALUE! | #VALUE! | 2025-08-04 |  |  | Complete | 0 | 2025/03/27 | 45700%
13 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | DM與手冊草稿 | 黃胤綸 | 2025-02-13 | #VALUE! | #VALUE! | 2025-02-13 |  |  | Complete | 0 | 2025/02/06 | 45700%
13.1 | M240101P1 | 首次生產-液體洩漏偵測器 | 第二次製作 | 蘇漢城 | 2025-07-08 | #VALUE! | #VALUE! | 2025-10-02 |  |  | Complete | 0 | 2025/07/02 | 45701%
13.2 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | GPX8 DVT-QA | 朱哲演 | 2025-02-27 | #VALUE! | #VALUE! | 2025-08-28 |  |  | Complete | 0 | 2025/08/06 | 45702%
13.3 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | SOP/加工重點 (半成品/成品/組裝/測試) | 魏暉恩 | 2025-02-27 | #VALUE! | #VALUE! | 2025-09-15 |  |  | Complete | 0 | 2025/08/25 | 45702%
13.4 | K240801R2 | PCB濕製程用插入式壓力感測器 | 工況試煉送樣 | 鄭珅易 | 2025-03-07 | #VALUE! | #VALUE! | 2025-08-28 |  |  | Complete | 0 | 2025/08/04 | 45709%
13.5 | K240801R2 | PCB濕製程用插入式壓力感測器 | QC工程表 | 鄭珅易 | 2025-02-27 | #VALUE! | #VALUE! | 2025-08-05 |  |  | Complete | 0 | 2025/08/05 | 45709%
13.6 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 專案任務排程與人力規劃 | 黃胤綸 | 2025-03-03 | #VALUE! | #VALUE! | 2025-03-05 |  |  | Complete | 0 | 2025/02/25 | 45714%
13.7 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 連板測試治具規劃與製作 | 賴慶樺 | 2025-03-21 | #VALUE! | #VALUE! | 2025-12-10 |  |  | Complete | 0 | 2025/08/04 | 45719%
13.8 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | QC工程表 | 李騏敬 | 2025-03-07 | #VALUE! | #VALUE! | 2025-08-26 |  |  | Complete | 0 | 2025/08/26 | 45719%
13.9 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 進料檢驗基準 | 李騏敬 | 2025-03-07 | #VALUE! | #VALUE! | 2025-05-15 |  |  | Complete | 0 | 2025/05/15 | 45719%
14 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 產品檢驗基準 | 李騏敬 | 2025-03-07 | #VALUE! | #VALUE! | 2025-08-11 |  |  | Complete | 0 | 2025/08/11 | 45719%
14.1 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 產品檢驗記錄 | 李騏敬 | 2025-03-07 | #VALUE! | #VALUE! | 2025-05-15 |  |  | Complete | 0 | 2025/05/15 | 45719%
14.2 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 機構圖面(元件/組裝/銘版) | 鄭貫中 | 2025-03-07 | #VALUE! | #VALUE! | 2025-10-20 |  |  | Complete | 0 | 2025/03/31 | 45719%
14.3 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | PCB圖面 | 許慧芝 | 2025-03-07 | #VALUE! | #VALUE! | 2025-03-10 |  |  | Complete | 0 | 2025/03/10 | 45719%
14.4 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 標籤貼紙(回覆標籤料號) | 黃胤綸 | 2025-03-07 | #VALUE! | #VALUE! | 2026-01-21 |  |  | Complete | 0 | 2025/07/15 | 45719%
14.5 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 產品規格比一覽表 | 黃胤綸 | 2025-03-05 | #VALUE! | #VALUE! | 2025-08-14 |  |  | Complete | 0 | 2025/04/14 | 45719%
14.6 | K240801R2 | PCB濕製程用插入式壓力感測器 | 進料檢驗基準 | 鄭珅易 | 2025-03-05 | #VALUE! | #VALUE! | 2025-08-05 |  |  | Complete | 0 | 2025/08/05 | 45719%
14.7 | K240801R2 | PCB濕製程用插入式壓力感測器 | 機構圖面(元件/組裝/銘版) | 張良琪 | 2025-03-07 | #VALUE! | #VALUE! | 2025-07-03 |  |  | Complete | 0 | 2025/03/03 | 45719%
14.8 | K240801R2 | PCB濕製程用插入式壓力感測器 | PCB 圖面 | 許慧芝 | 2025-03-07 | #VALUE! | #VALUE! | 2025-03-06 |  |  | Complete | 0 | 2025/03/06 | 45719%
14.9 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 工程試製 or 工況分析報告 | 蘇哲弘 | 2025-03-03 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/12/22 | 45719%
15 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 產品規格比較一覽表 (ISO表單：QR-C-22) | 蘇哲弘 | 2025-03-07 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/10/15 | 45719%
15.1 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 新產品成果內部產品 & 技術說明會 | 蘇哲弘 | 2025-03-07 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/03/20 | 45719%
15.2 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 研發開案企劃書 | 黃胤綸 | 2025-03-10 | #VALUE! | #VALUE! | 2025-03-12 |  |  | Complete | 0 | 2025/02/27 | 45720%
15.3 | K240801R2 | PCB濕製程用插入式壓力感測器 | 產品檢驗基準 | 鄭珅易 | 2025-03-12 | #VALUE! | #VALUE! | 2025-07-09 |  |  | Complete | 0 | 2025/07/09 | 45722%
15.4 | K240801R2 | PCB濕製程用插入式壓力感測器 | 產品檢驗記錄 | 鄭珅易 | 2025-03-12 | #VALUE! | #VALUE! | 2025-07-09 |  |  | Complete | 0 | 2025/07/09 | 45722%
15.5 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 研發內部審查會議記錄 | 陳威諭 | 2025-03-21 | #VALUE! | #VALUE! | 2025-03-31 |  |  | Complete | 0 | 2025/03/11 | 45726%
15.6 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 防爆認證報價單 | 陳威諭 | 2025-03-10 | #VALUE! | #VALUE! | 2025-03-11 |  |  | Complete | 0 | 2025/03/11 | 45726%
15.7 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 企劃開案企畫書 | 陳威諭 | 2025-03-21 | #VALUE! | #VALUE! | 2025-03-31 |  |  | Complete | 0 | 2025/03/31 | 45726%
15.8 | K240801R2 | PCB濕製程用插入式壓力感測器 | 開立內聯單請生管進行PCBA打件 (基本：A:20套 / K:50套 / M:100套，需在專案會議再次確認) | 張良琪 | 2025-04-09 | #VALUE! | #VALUE! | 2026-01-23 |  |  | Complete | 0 | 2025/12/31 | 45727%
15.9 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 研發內部審查會議記錄 | 黃胤綸 | 2025-03-11 | #VALUE! | #VALUE! | 2025-03-12 |  |  | Complete | 0 | 2025/03/11 | 45727%
16 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 提案審查會議記錄-跨部門 | 黃胤綸 | 2025-03-12 | #VALUE! | #VALUE! | 2025-03-19 |  |  | Complete | 0 | 2025/03/13 | 45728%
16.1 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 第二次生產 | 蘇漢城 | 2025-05-23 | #VALUE! | #VALUE! | 2025-10-02 |  |  | Complete | 0 | 2025/05/23 | 45729%
16.2 | K240801R2 | PCB濕製程用插入式壓力感測器 | 行銷確認首產及送樣規格及套數 | 張良琪 | 2025-04-11 | #VALUE! | #VALUE! | 2026-01-23 |  |  | Complete | 0 | 2025/12/31 | 45729%
16.3 | K240801R2 | PCB濕製程用插入式壓力感測器 | SOP/加工重點 (半成品/成品/組裝/測試) | 鄭珅易 | 2025-04-11 | #VALUE! | #VALUE! | 2025-08-05 |  |  | Complete | 0 | 2025/08/05 | 45729%
16.4 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38)防爆版目錄/手冊/訂購碼 | 黃胤綸 | 2025-03-19 | #VALUE! | #VALUE! | 2025-08-13 |  |  | Complete | 0 | 2025/05/15 | 45729%
16.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38)電路圖(3種電源板/控制板/顯示板/EEPROM板) | 黃胤綸 | 2025-03-19 | #VALUE! | #VALUE! | 2025-08-06 |  |  | Complete | 0 | 2025/05/15 | 45729%
16.6 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38) PCB(3種電源板/控制板/顯示板/EEPROM板) | 黃胤綸 | 2025-03-19 | #VALUE! | #VALUE! | 2025-08-06 |  |  | Complete | 0 | 2025/05/15 | 45729%
16.7 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38)機構關鍵零件UL黃卡與材質證明(非金屬類) | 鄭貫中 | 2025-03-28 | #VALUE! | #VALUE! | 2025-04-15 |  |  | Complete | 0 | 2025/03/21 | 45735%
16.8 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 連板測試治具測試軟體設計 | 李騏敬 | 2025-03-28 | #VALUE! | #VALUE! | 2026-01-13 |  |  | Complete | 0 | 2025/09/09 | 45740%
16.9 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38) BOM | 黃胤綸 | 2025-03-28 | #VALUE! | #VALUE! | 2025-08-06 |  |  | Complete | 0 | 2025/05/15 | 45740%
17 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38)半成品/成品圖面(含防爆對策與防爆鐵牌) | 鄭貫中 | 2025-03-28 | #VALUE! | #VALUE! | 2025-10-20 |  |  | Complete | 0 | 2025/05/26 | 45740%
17.1 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | SOP/加工重點(半成品/成品) | 李騏敬 | 2025-04-08 | #VALUE! | #VALUE! | 2025-04-02 |  |  | Complete | 0 | 2025/04/01 | 45747%
17.2 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 防爆樣品製作(包含提供防爆站測試/DVT驗證) | 李騏敬 | 2025-04-15 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45747% | 操作異常 | 任務異常 338 天
17.3 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 研發內部審查會議記錄 | 簡振芳 | 2025-04-01 | #VALUE! | #VALUE! | 2025-05-16 |  |  | Complete | 0 | 2025/04/01 | 45748%
17.4 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 產品驗證企劃書 | 陳威宏 | 2025-04-24 | #VALUE! | #VALUE! | 2025-05-15 |  |  | Complete | 0 | 2025/05/07 | 45749%
17.5 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 工程試製 | 黃胤綸 | 2025-04-22 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45756% | 操作異常 | 任務異常 331 天
17.6 | M240704R1 | 一體式夾管超音波流量計(DN25)[RD4] | 列印專案繳付清單(簽核)-SmartQ PLM026 | 蘇哲弘 | 2025-04-09 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2025/12/31 | 45756%
17.7 | K240801R2 | PCB濕製程用插入式壓力感測器 | 工程試製 or 工況分析報告 | 鄭珅易 | 2025-05-02 | #VALUE! | #VALUE! | 2026-03-12 |  |  | Complete | 0 | 2026/01/21 | 45761%
17.8 | K240801R2 | PCB濕製程用插入式壓力感測器 | 成品 EBOM(含零件庫存清單、採購建議書) | 張良琪 | 2025-04-18 | #VALUE! | #VALUE! | 2026-01-23 |  |  | Complete | 0 | 2026/01/23 | 45761%
17.9 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 樣品系統驗證,測試及問題解決(軟體/硬體/機構整合) | 李騏敬 | 2025-04-22 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45763% | 操作異常 | 任務異常 331 天
18 | K240801R2 | PCB濕製程用插入式壓力感測器 | 標籤貼紙 (回覆標籤版型料號) | 鄭珅易 | 2025-04-25 | #VALUE! | #VALUE! | 2025-08-21 |  |  | Complete | 0 | 2025/08/19 | 45768%
18.1 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 新產品技術說明會 | 黃胤綸 | 2025-04-25 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45770% | 操作異常 | 任務異常 328 天
18.2 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 防爆單位驗證進度追蹤 | 黃胤綸 | 2025-07-24 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2025/03/31 | 45770% | 操作異常 | 任務異常 238 天
18.3 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | DVT-QA測試 | 王琇眉 | 2025-05-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45771% | 操作異常 | 任務異常 310 天
18.4 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SCX5(SC38) Ta-Tp電路溫昇測試 | 李騏敬 | 2025-04-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45771% | 操作異常 | 任務異常 323 天
18.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | PCBA連板測試治具設計及製作(3種電源板/控制板/顯示板/EEPROM板) | 賴慶樺 | 2025-05-14 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45771% | 操作異常 | 任務異常 309 天
18.6 | D250101R1 | AI冷卻系統數位通訊溫度偵測器 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 黃胤綸 | 2025-04-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45775% | 操作異常 | 任務異常 323 天
18.7 | K240801R2 | PCB濕製程用插入式壓力感測器 | 產品規格比較一覽表 (ISO表單：QR-C-22) | 鄭珅易 | 2025-05-02 | #VALUE! | #VALUE! | 2025-08-08 |  |  | Complete | 0 | 2025/08/08 | 45775%
18.8 | K240801R2 | PCB濕製程用插入式壓力感測器 | 新產品成果內部產品 & 技術說明會 | 張良琪 | 2025-05-02 | #VALUE! | #VALUE! | 2025-12-30 |  |  | Complete | 0 | 2025/12/30 | 45775%
18.9 | K240101P1 | 首次生產-渦街流量計商品化 | PVT-QA測試驗證 | 陳威宏 | 2025-06-11 | #VALUE! | #VALUE! | 2025-05-12 |  |  | Complete | 0 | 2025/04/24 | 45777%
19 | K240801R2 | PCB濕製程用插入式壓力感測器 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 張良琪 | 2025-05-05 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45782% | 操作異常 | 任務異常 318 天
19.1 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 功能規格討論會議(機構審查) | 羅友彥 | 2025-05-13 | #VALUE! | #VALUE! | 2025-05-28 |  |  | Complete | 2026/03/05 | 2025/05/12 | 45789%
19.2 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 流程圖 | 羅友彥 | 2025-05-13 | #VALUE! | #VALUE! | 2025-05-28 |  |  | Complete | 2026/03/05 | 2025/05/12 | 45789%
19.3 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 2D組合圖面及3D爆炸圖面 | 羅友彥 | 2025-05-29 | #VALUE! | #VALUE! | 2025-06-05 |  |  | Complete | 2026/03/05 | 2025/05/12 | 45790%
19.4 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 2D零件尺寸圖面 | 羅友彥 | 2025-05-29 | #VALUE! | #VALUE! | 2025-06-05 |  |  | Complete | 2026/03/05 | 2025/05/12 | 45790%
19.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | QC工程表 | 李騏敬 | 2025-05-27 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45791% | 操作異常 | 任務異常 296 天
19.6 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 進料檢驗基準 | 李騏敬 | 2025-05-27 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45791% | 操作異常 | 任務異常 296 天
19.7 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 產品檢驗基準 | 李騏敬 | 2025-05-27 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45791% | 操作異常 | 任務異常 296 天
19.8 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 產品檢驗記錄 | 李騏敬 | 2025-05-27 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45791% | 操作異常 | 任務異常 296 天
19.9 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | PCB 圖面 | 許慧芝 | 2025-05-27 | #VALUE! | #VALUE! | 2025-06-10 |  |  | Complete | 0 | 2025/06/06 | 45791%
20 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | PCBA連板測試治具軟體設計及驗證(3種電源板/控制板/顯示板/EEPROM板) | 李奕澔 | 2025-05-21 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45792% | 操作異常 | 任務異常 302 天
20.1 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | SOP/加工重點 (半成品/成品/組裝/測試) | 李騏敬 | 2025-05-28 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45799% | 操作異常 | 任務異常 295 天
20.2 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 報價，零件表及成本分析表 | 羅友彥 | 2025-06-06 | #VALUE! | #VALUE! | 2025-06-05 |  |  | Complete | 2026/03/05 | 2025/05/20 | 45800%
20.3 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 第二次PVT-QA測試驗證 | 王琇眉 | 2025-07-07 | #VALUE! | #VALUE! | 2025-10-02 |  |  | Complete | 0 | 2025/06/13 | 45803%
20.4 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 測試樣品組裝 | 葉宏政 | 2025-06-03 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/13 | 45806%
20.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 標籤貼紙 (回覆標籤版型料號) | 黃胤綸 | 2025-06-05 | #VALUE! | #VALUE! | 2026-01-14 |  |  | Complete | 0 | 2025/07/02 | 45806%
20.6 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 樣品系統驗證,測試及問題解決(軟體/硬體/機構整合) | 葉宏政 | 2025-06-17 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/13 | 45812%
20.7 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 請購單簽核 | 羅友彥 | 2025-06-11 | #VALUE! | #VALUE! | 2025-06-30 |  |  | Complete | 2026/03/05 | 2025/05/27 | 45817%
20.8 | K240101P1 | 首次生產-渦街流量計商品化 | 第一次製作 | 蘇漢城 | 2025-10-13 | #VALUE! | #VALUE! | 2025-10-02 |  |  | Complete | 0 | 2025/09/17 | 45820%
20.9 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 零件加工 | 羅友彥 | 2025-06-27 | #VALUE! | #VALUE! | 2025-07-01 |  |  | Complete | 2026/03/05 | 2025/06/11 | 45821%
21 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 電路\程式設計 | 李育儒 | 2025-07-11 | #VALUE! | #VALUE! | 2025-08-15 |  |  | Complete | 2026/03/05 | 2025/05/27 | 45821%
21.1 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 控制軟體設計 | 郭景成 | 2025-07-18 | #VALUE! | #VALUE! | 2025-09-01 |  |  | Complete | 2026/03/05 | 2025/09/01 | 45821%
21.2 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 配電箱設計與製作 | 李育儒 | 2025-07-11 | #VALUE! | #VALUE! | 2025-08-15 |  |  | Complete | 2026/03/05 | 2025/05/27 | 45821%
21.3 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | DVT-QA測試 | 朱哲演 | 2025-06-24 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45826% | 操作異常 | 任務異常 268 天
21.4 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 型錄、DM與操作手冊草稿編修檔資料 (發起PLM提供給FAE) | 葉宏政 | 2025-06-18 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/23 | 45826%
21.5 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 產品檢驗基準 | 葉宏政 | 2025-06-30 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/24 | 45833%
21.6 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 產品檢驗記錄 | 葉宏政 | 2025-06-30 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/24 | 45833%
21.7 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 標籤貼紙 (回覆標籤版型料號) | 許慧芝 | 2025-07-01 | #VALUE! | #VALUE! | 2025-01-15 |  |  | Complete | 0 | 2025/01/13 | 45833%
21.8 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 測試治具設計及製作/移交清單 | 葉宏政 | 2025-07-15 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45833% | 操作異常 | 任務異常 247 天
21.9 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | SOP/加工重點 (半成品/成品/組裝/測試) | 葉宏政 | 2025-07-01 | #VALUE! | #VALUE! | 2025-07-11 |  |  | Complete | 0 | 2025/07/11 | 45833%
22 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 進料檢驗基準 | 葉宏政 | 2025-07-01 | #VALUE! | #VALUE! | 2025-07-02 |  |  | Complete | 0 | 2025/07/02 | 45833%
22.1 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | QC工程表 | 葉宏政 | 2025-06-30 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/24 | 45833%
22.2 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 機構組裝測試 | 羅友彥 | 2025-07-11 | #VALUE! | #VALUE! | 2025-08-11 |  |  | Complete | 2026/03/05 | 2025/06/30 | 45835%
22.3 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 工程試製 or 工況分析報告 | 楊瑞洋 | 2025-07-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45840% | 操作異常 | 任務異常 260 天
22.4 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 產品規格比較一覽表 (ISO表單：QR-C-22) | 葉宏政 | 2025-07-03 | #VALUE! | #VALUE! | 2025-07-03 |  |  | Complete | 0 | 2025/07/03 | 45840%
22.5 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 新產品成果內部產品 & 技術說明會 | 葉宏政 | 2025-07-08 | #VALUE! | #VALUE! | 2025-06-24 |  |  | Complete | 0 | 2025/06/20 | 45840%
22.6 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 機構圖面(元件/組裝/銘版) | 葉宏政 | 2025-07-08 | #VALUE! | #VALUE! | 2025-07-03 |  |  | Complete | 0 | 2025/07/01 | 45840%
22.7 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 樣品製作(PCBA) | 魏暉恩 | 2025-07-22 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45840% | 操作異常 | 任務異常 240 天
22.8 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 工況試煉送樣 | 葉宏政 | 2025-08-27 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45841% | 操作異常 | 任務異常 204 天
22.9 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | IP67改善 | 鄭貫中 | 2025-11-28 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45846% | 操作異常 | 任務異常 111 天
23 | M240101P1 | 首次生產-液體洩漏偵測器 | 第二次PVT-QA | 王琇眉 | 2025-08-19 | #VALUE! | #VALUE! | 2025-10-02 |  |  | Complete | 0 | 2025/08/01 | 45847%
23.1 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 整機測試驗證 | 羅友彥 | 2025-07-25 | #VALUE! | #VALUE! | 2025-11-18 |  |  | Complete | 2026/03/05 | 2025/07/28 | 45856%
23.2 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 樣品系統驗證,測試及問題解決(軟體/硬體/機構整合) | 陳俊儒 | 2025-08-12 | #VALUE! | #VALUE! | 2026-01-30 |  |  | Complete | 0 | 2025/10/13 | 45861%
23.3 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 操作說明書 | 羅友彥 | 2025-08-08 | #VALUE! | #VALUE! | 2025-09-12 |  |  | Complete | 2026/03/05 | 2025/08/12 | 45863%
23.4 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 機構圖面(元件/組裝/銘版) | 鄭貫中 | 2025-08-07 | #VALUE! | #VALUE! | 2025-10-20 |  |  | Complete | 0 | 2025/09/25 | 45863%
23.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 防爆測試報告 | 黃胤綸 | 2025-08-07 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45863% | 操作異常 | 任務異常 224 天
23.6 | D250801R1 | SCX6标准/加长型技转 | 文件審查 (BOM.圖面.SOP) | 郑仁春 | 2025-08-08 | #VALUE! | #VALUE! | 2025-08-07 |  |  | Complete | 0 | 2025/08/01 | 45870%
23.7 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 試產技術移轉會議/技術移轉時程表 | 羅友彥 | 2025-08-07 | #VALUE! | #VALUE! | 2025-09-19 |  |  | Complete | 2026/03/05 | 2025/09/19 | 45870%
23.8 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 小量試產/產線驗收 | 羅友彥 | 2025-08-11 | #VALUE! | #VALUE! |  |  |  | Active | 2026/03/05 | 2026/03/03 | 45870% | 操作異常 | 任務異常 220 天
23.9 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 圖面資料、採購資料、安裝手冊、操作說明書發行、驗收報告 | 羅友彥 | 2025-08-11 | #VALUE! | #VALUE! | 2025-10-01 |  |  | Complete | 2026/03/05 | 2025/08/11 | 45870%
24 | D250301R1 | EPD電磁流量計技转 | 总部产品资料申请（BOM、图面、SOP） | 汪佳凯 | 2025-08-21 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/08/04 | 45873%
24.1 | D250701R1 | EGX5标准型技转 | 文件審查 (BOM.圖面.SOP) | 汪佳凯 | 2025-09-01 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/08/04 | 45873%
24.2 | D250701R1 | EGX5标准型技转 | 总部产品资料申请（BOM、图面、SOP） | 汪佳凯 | 2025-08-21 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/08/04 | 45873%
24.3 | D250701R1 | EGX5标准型技转 | 产品导入方案评估 | 汪佳凯 | 2025-08-21 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/08/04 | 45873%
24.4 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 工程試製 or 工況分析報告 | 黃胤綸 | 2025-09-18 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45877% | 操作異常 | 任務異常 182 天
24.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 防爆證書 | 黃胤綸 | 2025-08-21 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45877% | 操作異常 | 任務異常 210 天
24.6 | D250801R1 | SCX6标准/加长型技转 | 物料采购 | 郑仁春 | 2025-10-17 | #VALUE! | #VALUE! | 2025-10-16 |  |  | Complete | 0 | 2025/08/08 | 45880%
24.7 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | DVT-QA樣機EOM建立 | 魏暉恩 | 2025-08-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45882% | 操作異常 | 任務異常 218 天
24.8 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 型錄、DM與操作手冊草稿編修檔資料 (發起PLM提供給FAE) | 陳俊儒 | 2025-08-20 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45883% | 操作異常 | 任務異常 211 天
24.9 | D250802R1 | 申請量桶量槽製作資格 | 量桶量槽製作資格申請評估 | 何昆達 | 2025-08-18 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/18 | 45887%
25 | D250802R1 | 申請量桶量槽製作資格 | 購置標準器(量桶5L、10L、20L、50L) | 何昆達 | 2025-08-19 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/19 | 45888%
25.1 | D250802R1 | 申請量桶量槽製作資格 | 標準量桶取得校正報告 | 何昆達 | 2025-08-20 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/20 | 45889%
25.2 | M240101P1 | 首次生產-液體洩漏偵測器 | 熱縮套脫落改善 | 蘇漢城 | 2025-12-01 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45889% | 操作異常 | 任務異常 108 天
25.3 | D250802R1 | 申請量桶量槽製作資格 | 申請標準器(流量計1m3/h及10m3/h以上各一只) | 何昆達 | 2025-08-25 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/21 | 45890%
25.4 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | DVT-QA測試 | 陳威宏 | 2025-09-10 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45890% | 操作異常 | 任務異常 190 天
25.5 | D250301R1 | EPD電磁流量計技转 | 产品导入方案评估 | 汪佳凯 | 2025-09-10 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/08/22 | 45891%
25.6 | D250802R1 | 申請量桶量槽製作資格 | 標準流量計取得校正報告 | 何昆達 | 2025-08-26 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/26 | 45895%
25.7 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 評估首產及送樣規格及套數 | 郭俊元 | 2025-09-15 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45895% | 操作異常 | 任務異常 185 天
25.8 | D250802R1 | 申請量桶量槽製作資格 | 申請度量衡業營業許可程序評估 | 何昆達 | 2025-08-27 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/27 | 45896%
25.9 | D250802R1 | 申請量桶量槽製作資格 | 度量衡業營業許可項目變更相關資料匯整及申請 | 何昆達 | 2025-08-28 | #VALUE! | #VALUE! | 2025-08-29 |  |  | Complete | 0 | 2025/08/28 | 45897%
26 | M240804R1 | PVD二口二位閥展型(DN15、DN20) | 列印專案繳付清單(簽核)-SmartQ PLM026 | 葉宏政 | 2025-08-28 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45897% | 操作異常 | 任務異常 203 天
26.1 | D250802R1 | 申請量桶量槽製作資格 | 提出度量衡業營業許可項目變更申請 | 何昆達 | 2025-08-29 | #VALUE! | #VALUE! | 2025-09-08 |  |  | Complete | 0 | 2025/08/29 | 45898%
26.2 | D250802R1 | 申請量桶量槽製作資格 | 度量衡業營業許可項目變更申請文件審核(標檢局) | 何昆達 | 2025-09-12 | #VALUE! | #VALUE! | 2025-10-29 |  |  | Complete | 0 | 2025/10/03 | 45901%
26.3 | D250701R1 | EGX5标准型技转 | 研发试产，制作样品 | 汪佳凯 | 2025-10-16 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/09/02 | 45902%
26.4 | D250301R1 | EPD電磁流量計技转 | 文件審查 (BOM.圖面.SOP) | 汪佳凯 | 2025-10-01 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/09/11 | 45911%
26.5 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 開立內聯單請廠務進行PCBA打件 (基本：A:20套 / K:50套 / M:100套，需在專案會議再次確認) | 周家儀 | 2025-09-11 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45911% | 操作異常 | 任務異常 189 天
26.6 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 產品檢驗基準 | 魏暉恩 | 2025-09-22 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45911% | 操作異常 | 任務異常 178 天
26.7 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 產品檢驗記錄 | 魏暉恩 | 2025-09-22 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45911% | 操作異常 | 任務異常 178 天
26.8 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 測試治具設計及製作/移交清單 | 魏暉恩 | 2025-10-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45911% | 操作異常 | 任務異常 157 天
26.9 | D250802R1 | 申請量桶量槽製作資格 | 實地查核(標檢局) | 何昆達 | 2025-09-15 | #VALUE! | #VALUE! | 2025-11-20 |  |  | Complete | 0 | 2025/10/31 | 45915%
27 | D250802R1 | 申請量桶量槽製作資格 | 核發度量衡業營業許可執照(標檢局) | 何昆達 | 2025-09-30 | #VALUE! | #VALUE! | 2025-11-20 |  |  | Complete | 0 | 2025/11/11 | 45916%
27.1 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 工況試煉送樣 | 陳俊儒 | 2025-09-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45916% | 操作異常 | 任務異常 170 天
27.2 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | QC工程表 | 魏暉恩 | 2025-09-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45918% | 操作異常 | 任務異常 170 天
27.3 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 進料檢驗基準 | 魏暉恩 | 2025-09-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45918% | 操作異常 | 任務異常 170 天
27.4 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 李騏敬 | 2025-09-23 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45919% | 操作異常 | 任務異常 177 天
27.5 | M250201C1 | 工業爆炸環境防爆型音叉感測器 | 證書上傳BPM | 李騏敬 | 2025-09-23 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45919% | 操作異常 | 任務異常 177 天
27.6 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 標籤貼紙 (回覆標籤版型料號) | 魏暉恩 | 2025-09-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45923% | 操作異常 | 任務異常 170 天
27.7 | D250802R1 | 申請量桶量槽製作資格 | 度量衡業營業許可執照正本繳交至財務處(玉香)保管 | 何昆達 | 2025-10-01 | #VALUE! | #VALUE! | 2025-11-20 |  |  | Complete | 0 | 2025/11/17 | 45931%
27.8 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 產品規格比較一覽表 (ISO表單：QR-C-22) | 陳俊儒 | 2025-10-08 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45931% | 操作異常 | 任務異常 162 天
27.9 | D250301R1 | EPD電磁流量計技转 | 研发试产：产品（旧款）拆装换新作业 | 汪佳凯 | 2025-10-09 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/09/22 | 45932%
28 | D250802R1 | 申請量桶量槽製作資格 | 申請量桶量槽標定(標檢局)-50L+300L為一組，共三組6個 | 何昆達 | 2025-12-01 | #VALUE! | #VALUE! | 2025-12-10 |  |  | Complete | 0 | 2025/12/01 | 45932%
28.1 | D250301R1 | EPD電磁流量計技转 | 旧品换新作业标准建立 | 汪佳凯 | 2025-10-31 | #VALUE! | #VALUE! | 2025-11-11 |  |  | Complete | 0 | 2025/09/26 | 45943%
28.2 | K240101P1 | 首次生產-渦街流量計商品化 | PVT-QA測試驗證 | 王琇眉 | 2025-11-25 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 45944% | 操作異常 | 任務異常 114 天
28.3 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | SOP/加工重點 (半成品/成品/組裝/測試) | 魏暉恩 | 2025-10-23 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45944% | 操作異常 | 任務異常 147 天
28.4 | D250701R1 | EGX5标准型技转 | 開立工單(工單、預計生產時間) | 汪佳凯 | 2025-10-21 | #VALUE! | #VALUE! | 2025-10-19 |  |  | Complete | 0 | 2025/10/17 | 45947%
28.5 | D250801R1 | SCX6标准/加长型技转 | 产品试生产（研发生产、样品制做） | 郑仁春 | 2025-11-07 | #VALUE! | #VALUE! | 2025-11-10 |  |  | Complete | 0 | 2025/10/20 | 45950%
28.6 | D250701R1 | EGX5标准型技转 | 缺料採購(採購單) | 汪佳凯 | 2025-11-05 | #VALUE! | #VALUE! | 2025-12-06 |  |  | Complete | 0 | 2025/10/22 | 45952%
28.7 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 工程試製 or 工況分析報告 | 楊瑞洋 | 2025-12-10 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45957% | 操作異常 | 任務異常 99 天
28.8 | D250301R1 | EPD電磁流量計技转 | 旧品换新作业移转车间生产 | 汪佳凯 | 2025-11-20 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45964% | 操作異常 | 任務異常 119 天
28.9 | M240803P1 | EGX5防腐型技转 | 文件審查 (BOM.圖面.SOP) | 汪佳凯 | 2025-11-05 | #VALUE! | #VALUE! | 2025-11-06 |  |  | Complete | 0 | 2025/11/03 | 45964%
29 | D250701R1 | EGX5标准型技转 | 品質檢驗(檢驗紀錄、基準) | 汪佳凯 | 2025-11-17 | #VALUE! | #VALUE! | 2025-11-17 |  |  | Complete | 0 | 2025/11/17 | 45967%
29.1 | M240803P1 | EGX5防腐型技转 | 电路Layout图 | 許慧芝 | 2025-11-10 | #VALUE! | #VALUE! | 2026-01-07 |  |  | Complete | 0 | 2026/01/07 | 45967%
29.2 | M251001R1 | SDX緊湊型光電開關設計 | 時程規劃/人員安排 | 彭志豪 | 2025-11-07 | #VALUE! | #VALUE! | 2025-11-06 |  |  | Complete | 0 | 2025/11/06 | 45967%
29.3 | D250801R1 | SCX6标准/加长型技转 | Copy of 物料采购 | 0 | 2025-11-21 | #VALUE! | #VALUE! | 2025-12-02 |  |  | Active | 0 | 2025/11/12 | 45971%
29.4 | M251001R1 | SDX緊湊型光電開關設計 | 開發企劃書 | 彭志豪 | 2025-11-21 | #VALUE! | #VALUE! | 2025-12-01 |  |  | Complete | 0 | 2025/11/10 | 45971%
29.5 | M240803P1 | EGX5防腐型技转 | PVT技轉會議紀錄 | 汪佳凯 | 2025-11-13 | #VALUE! | #VALUE! | 2025-10-30 |  |  | Complete | 0 | 2025/10/31 | 45972%
29.6 | M240803P1 | EGX5防腐型技转 | 開立工單(工單、預計生產時間) | 汪佳凯 | 2025-11-18 | #VALUE! | #VALUE! | 2025-11-17 |  |  | Complete | 0 | 2025/11/13 | 45975%
29.7 | D250701R1 | EGX5标准型技转 | 首次生產(生產管制表) | 汪佳凯 | 2025-11-28 | #VALUE! | #VALUE! | 2025-10-30 |  |  | Complete | 0 | 2025/10/31 | 45979%
29.8 | M240803P1 | EGX5防腐型技转 | 缺料採購(採購單) | 汪佳凯 | 2025-12-02 | #VALUE! | #VALUE! | 2025-12-04 |  |  | Complete | 0 | 2025/11/27 | 45980%
29.9 | D250301R1 | EPD電磁流量計技转 | 研发试产，制作样品（全新产品） | 汪佳凯 | 2025-12-10 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2025/12/10 | 45982% | 操作異常 | 任務異常 99 天
30 | D250801R1 | SCX6标准/加长型技转 | 首次生產(生產管制表) | 郑仁春 | 2025-12-18 | #VALUE! | #VALUE! | 2026-01-13 |  |  | Active | 0 | 2025/12/04 | 45985%
30.1 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 商品企劃書+QFD (ISO表單：QR-D-19) | 吳志嘉 | 2025-12-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45986% | 操作異常 | 任務異常 79 天
30.2 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 專案時程規劃 | 王瀚霆 | 2025-11-25 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45986% | 操作異常 | 任務異常 114 天
30.3 | K240101P1 | 首次生產-渦街流量計商品化 | 設變 | 簡振芳 | 2025-12-02 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 45987% | 操作異常 | 任務異常 107 天
30.4 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | CNPA49第4版螺紋干擾器1、2、3型製作 | 王瀚霆 | 2025-12-08 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45987% | 操作異常 | 任務異常 101 天
30.5 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 研發開案企劃書 (ISO表單：QR-C-07) | 王瀚霆 | 2025-12-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45988% | 操作異常 | 任務異常 107 天
30.6 | M251001R1 | SDX緊湊型光電開關設計 | 研發內部審查會議記錄 | 彭志豪 | 2025-11-28 | #VALUE! | #VALUE! | 2025-12-01 |  |  | Complete | 0 | 2025/11/28 | 45989%
30.7 | D250701R1 | EGX5标准型技转 | PVT-QA測試驗證 | 汪佳凯 | 2026-01-13 | #VALUE! | #VALUE! | 2026-01-15 |  |  | Complete | 0 | 2025/12/19 | 45992%
30.8 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 第三次生產 | 蘇漢城 | 2026-01-12 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 45992% | 操作異常 | 任務異常 66 天
30.9 | D250802R1 | 申請量桶量槽製作資格 | 量桶量槽校正(工研院)--50L+300L為一組，共三組6個 | 何昆達 | 2026-01-28 | #VALUE! | #VALUE! | 2026-02-26 |  |  | Complete | 0 | 2026/02/03 | 45993%
31 | M240101P1 | 首次生產-液體洩漏偵測器 | 第三次製作 | 蘇漢城 | 2026-01-13 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 45993% | 操作異常 | 任務異常 65 天
31.1 | K240101P1 | 首次生產-渦街流量計商品化 | SOP修正 | 蘇漢城 | 2025-12-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 45994% | 操作異常 | 任務異常 100 天
31.2 | M240803P1 | EGX5防腐型技转 | 品質檢驗(檢驗紀錄、基準) | 汪佳凯 | 2025-12-12 | #VALUE! | #VALUE! | 2025-12-03 |  |  | Complete | 0 | 2025/12/03 | 45994%
31.3 | M251001R1 | SDX緊湊型光電開關設計 | 跨部門會議 | 彭志豪 | 2025-12-03 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/02/06 | 45994% | 操作異常 | 任務異常 106 天
31.4 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 研發內部審查會議記錄 | 王瀚霆 | 2025-12-04 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45995% | 操作異常 | 任務異常 105 天
31.5 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 研發企劃會議紀錄 | 王瀚霆 | 2025-12-05 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 45996% | 操作異常 | 任務異常 104 天
31.6 | E250101I1 | SQ壓力開關調校設備(單顆+步進馬達) | 調整流程重新規劃驗證 | 羅友彥 | 2025-12-16 | #VALUE! | #VALUE! | 2026-03-02 |  |  | Complete | 2026/03/05 | 2026/01/27 | 45999%
31.7 | K240101P1 | 首次生產-渦街流量計商品化 | 結案會議紀錄 | 蘇漢城 | 2025-12-10 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46001% | 操作異常 | 任務異常 99 天
31.8 | D250301R1 | EPD電磁流量計技转 | 開立工單(工單、預計生產時間) | 汪佳凯 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46002% | 操作異常 | 任務異常 80 天
31.9 | K240101P1 | 首次生產-渦街流量計商品化 | 結案報告 | 蘇漢城 | 2025-12-24 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46002% | 操作異常 | 任務異常 85 天
32 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 新產品成果內部產品 & 技術說明會 | 陳俊儒 | 2025-12-17 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46002% | 操作異常 | 任務異常 92 天
32.1 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 測試項目規劃彙整 | 王瀚霆 | 2025-12-19 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46006% | 操作異常 | 任務異常 90 天
32.2 | M240803P1 | EGX5防腐型技转 | 首次生產(生產管制表) | 汪佳凯 | 2025-12-26 | #VALUE! | #VALUE! | 2025-12-23 |  |  | Complete | 0 | 2025/12/15 | 46006%
32.3 | M251201R1 | 緊湊型渦街流量計導入專案 | 研發內部審查會議記錄 | 陳奕宏 | 2025-12-15 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46006% | 操作異常 | 任務異常 94 天
32.4 | M251201R1 | 緊湊型渦街流量計導入專案 | 產品開發風險評估表 | 陳奕宏 | 2025-12-16 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46007% | 操作異常 | 任務異常 93 天
32.5 | M251201R1 | 緊湊型渦街流量計導入專案 | 提案審查會議記錄-跨部門 (推廣型號及數量) | 陳奕宏 | 2025-12-17 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46008% | 操作異常 | 任務異常 92 天
32.6 | M250301R1 | 軌道型顯示器夾管式超音波流量計 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 陳俊儒 | 2025-12-18 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 91 天
32.7 | M251201R1 | 緊湊型渦街流量計導入專案 | 產品驗證企劃書 | 王琇眉 | 2025-12-24 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 85 天
32.8 | M251201R1 | 緊湊型渦街流量計導入專案 | 產品功能驗證計畫 | 陳奕宏 | 2025-12-24 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 85 天
32.9 | M251201R1 | 緊湊型渦街流量計導入專案 | 樣品請購(塑膠*3、金屬*4) | 陳奕宏 | 2026-01-09 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 69 天
33 | M251201R1 | 緊湊型渦街流量計導入專案 | 驗證治具設計(DN10、DN15、DN20、DN25、DN32夾具) | 0 | 2025-12-24 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 85 天
33.1 | M251201R1 | 緊湊型渦街流量計導入專案 | 型錄、DM與操作手冊草稿編修檔資料 (發起PLM提供給FAE) | 鄭珅易 | 2025-12-18 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 91 天
33.2 | M251201R1 | 緊湊型渦街流量計導入專案 | 預算書(人力預算、設備建置、競爭者樣機購置) | 陳奕宏 | 2025-12-18 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46009% | 操作異常 | 任務異常 91 天
33.3 | D250801R1 | SCX6标准/加长型技转 | PVT-QA測試驗證 | 郑仁春 | 2025-12-26 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/01/23 | 46010% | 操作異常 | 任務異常 83 天
33.4 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 代客戶申請ML及TR | 陳威諭 | 2025-12-26 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2025/12/23 | 46010% | 操作異常 | 任務異常 83 天
33.5 | M251201R1 | 緊湊型渦街流量計導入專案 | 標籤貼紙 (回覆標籤版型料號) | 鄭珅易 | 2025-12-19 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46010% | 操作異常 | 任務異常 90 天
33.6 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 產品驗證企劃書 | 朱哲演 | 2026-01-15 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 63 天
33.7 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 世代1-CNPA49第4版測試(軟體/硬體/機構整合) | 何昆達 | 2026-01-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 65 天
33.8 | M251001R1 | SDX緊湊型光電開關設計 | PCBA量產測試治具設計及製作(連板測試治具) | 陳威諭 | 2026-01-20 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2025/12/26 | 46013% | 操作異常 | 任務異常 58 天
33.9 | M251001R1 | SDX緊湊型光電開關設計 | QC工程表 | 莊廉琯 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 80 天
34 | M251001R1 | SDX緊湊型光電開關設計 | 進料檢驗基準 | 莊廉琯 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/02/12 | 46013% | 操作異常 | 任務異常 80 天
34.1 | M251001R1 | SDX緊湊型光電開關設計 | 產品檢驗基準 | 莊廉琯 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 80 天
34.2 | M251001R1 | SDX緊湊型光電開關設計 | 產品檢驗記錄 | 莊廉琯 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 80 天
34.3 | M251001R1 | SDX緊湊型光電開關設計 | PCB 圖面 | 許慧芝 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/02/12 | 46013% | 操作異常 | 任務異常 80 天
34.4 | M251001R1 | SDX緊湊型光電開關設計 | 標籤貼紙 (回覆標籤版型料號) | 彭志豪 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 80 天
34.5 | M251001R1 | SDX緊湊型光電開關設計 | 成品量產測試治具設計及製作(一次5PCS) | 莊廉琯 | 2026-01-20 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46013% | 操作異常 | 任務異常 58 天
34.6 | M251001R1 | SDX緊湊型光電開關設計 | 生產組裝治具設計及製作(金屬型探頭鉚合治具、太陽片+成品組裝治具) | 陳威瑜 | 2026-01-20 | #VALUE! | #VALUE! | 2026-01-15 |  |  | Complete | 0 | 2026/01/05 | 46013%
34.7 | D250801R1 | SCX6标准/加长型技转 | 設變 | 郑仁春 | 2025-12-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46017% | 操作異常 | 任務異常 80 天
34.8 | K240101P1 | 首次生產-渦街流量計商品化 | 結案文件審查 | 余依錚 | 2025-12-30 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46017% | 操作異常 | 任務異常 79 天
34.9 | M251201R1 | 緊湊型渦街流量計導入專案 | 驗證治具製作 | 0 | 2026-01-09 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46017% | 操作異常 | 任務異常 69 天
35 | M240803P1 | EGX5防腐型技转 | PVT-QA測試驗證 | 汪佳凯 | 2026-02-09 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2025/12/25 | 46020% | 操作異常 | 任務異常 38 天
35.1 | M251201C1 | GPX 申請UL-61010認證 | 專案排程 | 賴慶樺 | 2026-01-07 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2026/01/02 | 46020%
35.2 | D250301R1 | EPD電磁流量計技转 | 缺料採購(採購單) | 汪佳凯 | 2026-01-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46021% | 操作異常 | 任務異常 65 天
35.3 | D250801R1 | SCX6标准/加长型技转 | SOP修正 | 郑仁春 | 2025-12-31 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46021% | 操作異常 | 任務異常 78 天
35.4 | K240101P1 | 首次生產-渦街流量計商品化 | MP發行 | 余依錚 | 2026-01-02 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46022% | 操作異常 | 任務異常 76 天
35.5 | K251101R1 | 精巧型電磁流量計 | 研發內部審查會議記錄 | 魏暉恩 | 2026-01-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46024% | 操作異常 | 任務異常 76 天
35.6 | K251101R1 | 精巧型電磁流量計 | 提案審查會議記錄 (跨部門) | 魏暉恩 | 2026-01-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46024% | 操作異常 | 任務異常 76 天
35.7 | K251101R1 | 精巧型電磁流量計 | 商品企劃書+QFD (ISO表單：QR-D-19) | 吳志嘉 | 2026-01-05 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46027% | 操作異常 | 任務異常 73 天
35.8 | K251101R1 | 精巧型電磁流量計 | 先導樣機性能報告 (樣機A) | 楊瑞洋 | 2026-01-06 | #VALUE! | #VALUE! | 2026-01-29 |  |  | Complete | 0 | 2025/10/13 | 46028%
35.9 | K251101R1 | 精巧型電磁流量計 | 先導樣機測試/拆解報告 (樣機B) | 魏暉恩 | 2026-01-08 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46028% | 操作異常 | 任務異常 70 天
36 | M251201C1 | GPX 申請UL-61010認證 | 預算書(人力預算、設備建置、競爭者樣機購置) | 賴慶樺 | 2026-01-09 | #VALUE! | #VALUE! | 2026-01-08 |  |  | Complete | 0 | 2026/01/08 | 46030%
36.1 | D250801R1 | SCX6标准/加长型技转 | 結案文件審查 | 郑仁春 | 2026-01-12 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46031% | 操作異常 | 任務異常 66 天
36.2 | K251101R1 | 精巧型電磁流量計 | 研發開案企劃書+預算書 (ISO表單：QR-C-07) | 魏暉恩 | 2026-01-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46031% | 操作異常 | 任務異常 65 天
36.3 | M251201C1 | GPX 申請UL-61010認證 | 確認認證等級 | 賴慶樺 | 2026-01-16 | #VALUE! | #VALUE! | 2026-02-05 |  |  | Complete | 0 | 2026/01/16 | 46034%
36.4 | M251201C1 | GPX 申請UL-61010認證 | CSA認證單位-GPX認證報價 | 賴慶樺 | 2026-01-16 | #VALUE! | #VALUE! | 2026-02-05 |  |  | Complete | 0 | 2026/01/16 | 46034%
36.5 | M251201C1 | GPX 申請UL-61010認證 | GPX簽訂認證合約 | 賴慶樺 | 2026-01-14 | #VALUE! | #VALUE! | 2026-02-05 |  |  | Complete | 0 | 2026/01/14 | 46034%
36.6 | M251201R1 | 緊湊型渦街流量計導入專案 | 樣品性能驗證 | 陳奕宏 | 2026-01-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46034% | 操作異常 | 任務異常 55 天
36.7 | D250801R1 | SCX6标准/加长型技转 | MP發行 | 郑仁春 | 2026-01-14 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46035% | 操作異常 | 任務異常 64 天
36.8 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 第三次PVT-QA驗證 | 王琇眉 | 2026-02-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46035% | 操作異常 | 任務異常 24 天
36.9 | K251101R1 | 精巧型電磁流量計 | 研發企劃會議紀錄 | 魏暉恩 | 2026-01-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46035% | 操作異常 | 任務異常 65 天
37 | D250301R1 | EPD電磁流量計技转 | 品質檢驗(檢驗紀錄、基準) | 汪佳凯 | 2026-01-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46036% | 操作異常 | 任務異常 55 天
37.1 | D250701R1 | EGX5标准型技转 | 設變 | 汪佳凯 | 2026-01-22 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46036% | 操作異常 | 任務異常 56 天
37.2 | M240101P1 | 首次生產-液體洩漏偵測器 | 第三次PVT-QA | 王琇眉 | 2026-02-24 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46036% | 操作異常 | 任務異常 23 天
37.3 | M251201C1 | GPX 申請UL-61010認證 | CSA認證單位-GPX產品討論 | 賴慶樺 | 2026-01-27 | #VALUE! | #VALUE! | 2026-02-12 |  |  | Complete | 0 | 2026/01/21 | 46036%
37.4 | K251101R1 | 精巧型電磁流量計 | 產品驗證企劃書 | 王琇眉 | 2026-02-23 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46037% | 操作異常 | 任務異常 24 天
37.5 | D260102R1 | 2026年程式碼審查1st | EPD30 | 蕭金椿 | 2026-01-23 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46041% | 操作異常 | 任務異常 55 天
37.6 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 樣品系統驗證,測試及問題解決(軟體/硬體/機構整合) | 許博元 | 2026-02-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2025/12/08 | 46042% | 操作異常 | 任務異常 45 天
37.7 | D250701R1 | EGX5标准型技转 | SOP修正 | 汪佳凯 | 2026-02-02 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46045% | 操作異常 | 任務異常 45 天
37.8 | D250301R1 | EPD電磁流量計技转 | 首次生產(生產管制表) | 汪佳凯 | 2026-02-05 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46048% | 操作異常 | 任務異常 42 天
37.9 | D260102R1 | 2026年程式碼審查1st | EPH | 張文魁 | 2026-01-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46048% | 操作異常 | 任務異常 48 天
38 | M251201R1 | 緊湊型渦街流量計導入專案 | DVT-QA測試 | 王琇眉 | 2026-02-06 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46048% | 操作異常 | 任務異常 41 天
38.1 | M251201C1 | GPX 申請UL-61010認證 | GPX產品資料整理提供及更新 | 賴慶樺 | 2026-02-23 | #VALUE! | #VALUE! | 2026-02-26 |  |  | Complete | 0 | 2026/01/28 | 46049%
38.2 | M251001R1 | SDX緊湊型光電開關設計 | 機構圖面(元件/組裝/銘版) | 王瀚霆 | 2026-02-03 | #VALUE! | #VALUE! | 2026-02-11 |  |  | Complete | 0 | 2026/02/11 | 46050%
38.3 | M251001R1 | SDX緊湊型光電開關設計 | SOP/加工重點 (半成品/成品/組裝/測試) | 莊廉琯 | 2026-01-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/02/06 | 46050% | 操作異常 | 任務異常 48 天
38.4 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 世代2-CNPA49第4版測試(軟體/硬體/機構整合)與改善 | 何昆達 | 2026-02-25 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46051% | 操作異常 | 任務異常 22 天
38.5 | M251001R1 | SDX緊湊型光電開關設計 | DVT-QA測試 | 王琇眉 | 2026-02-11 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46051% | 操作異常 | 任務異常 36 天
38.6 | K231101P1 | 首次生產-AI伺服器用熱質流量計 | 結案報告 | 蘇漢城 | 2026-02-12 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46052% | 操作異常 | 任務異常 35 天
38.7 | D260102R1 | 2026年程式碼審查1st | EPR | 張文魁 | 2026-02-06 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46055% | 操作異常 | 任務異常 41 天
38.8 | D260103R1 | HART dd先期研究案 | HART dd file文件蒐集閱讀 | 蕭金椿 | 2026-03-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46055% | 操作異常 | 任務異常 17 天
38.9 | D260103R1 | HART dd先期研究案 | HART dd file工具列表請購 | 蕭金椿 | 2026-03-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46055% | 操作異常 | 任務異常 17 天
39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
39.1 | M251201C1 | GPX 申請UL-61010認證 | GPX文件初審 | 賴慶樺 | 2026-03-02 | #VALUE! | #VALUE! | 2026-02-26 |  |  | Complete | 0 | 2026/02/09 | 46055%
39.2 | D250701R1 | EGX5标准型技转 | 結案文件審查 | 汪佳凯 | 2026-02-05 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46056% | 操作異常 | 任務異常 42 天
39.3 | D250301R1 | EPD電磁流量計技转 | PVT-QA測試驗證 | 汪佳凯 | 2026-03-27 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46059% | 操作異常
39.4 | D250701R1 | EGX5标准型技转 | MP發行 | 汪佳凯 | 2026-02-24 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46059% | 操作異常 | 任務異常 23 天
39.5 | D260102R1 | 2026年程式碼審查1st | EPT | 張政崙 | 2026-02-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46062% | 操作異常 | 任務異常 34 天
39.6 | M251201C1 | GPX 申請UL-61010認證 | GPX 相關文件修訂 | 賴慶樺 | 2026-03-02 | #VALUE! | #VALUE! | 2026-02-26 |  |  | Complete | 0 | 2026/02/12 | 46062%
39.7 | M251201R1 | 緊湊型渦街流量計導入專案 | 工況試煉送樣 | 陳奕宏 | 2026-02-13 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46062% | 操作異常 | 任務異常 34 天
39.8 | M251201R1 | 緊湊型渦街流量計導入專案 | QC工程表 | 陳奕宏 | 2026-02-10 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46062% | 操作異常 | 任務異常 37 天
39.9 | M240803P1 | EGX5防腐型技转 | 設變 | 汪佳凯 | 2026-02-23 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46063% | 操作異常 | 任務異常 24 天
40 | M251201R1 | 緊湊型渦街流量計導入專案 | 進料檢驗基準 (表單QR-B-15) | 鄭珅易 | 2026-02-11 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46064% | 操作異常 | 任務異常 36 天
40.1 | M251001R1 | SDX緊湊型光電開關設計 | 工況試煉送樣 | 彭志豪 | 2026-03-05 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46065% | 操作異常 | 任務異常 14 天
40.2 | M251001R1 | SDX緊湊型光電開關設計 | 工程試製 or 工況分析報告 | 彭志豪 | 2026-04-09 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46065% | 操作異常
40.3 | M251201R1 | 緊湊型渦街流量計導入專案 | 產品檢驗基準 | 鄭珅易 | 2026-02-12 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46065% | 操作異常 | 任務異常 35 天
40.4 | M251201R1 | 緊湊型渦街流量計導入專案 | 產品檢驗記錄 | 鄭珅易 | 2026-02-12 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46065% | 操作異常 | 任務異常 35 天
40.5 | K231101P1 | 首次生產-AI伺服器用熱質流量計 | 結案文件審查 | 余依錚 | 2026-02-26 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46066% | 操作異常 | 任務異常 21 天
40.6 | M251201R1 | 緊湊型渦街流量計導入專案 | SOP (測試) | 鄭珅易 | 2026-02-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46066% | 操作異常 | 任務異常 24 天
40.7 | D260102R1 | 2026年程式碼審查1st | EPU1D01_Dinrail | 蕭金椿 | 2026-03-02 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46069% | 操作異常 | 任務異常 17 天
40.8 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | DVT-QA測試 | 王琇眉 | 2026-03-13 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46076% | 操作異常 | 任務異常 6 天
40.9 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 設變 | 蘇漢城 | 2026-03-02 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46077% | 操作異常 | 任務異常 17 天
41 | M240803P1 | EGX5防腐型技转 | SOP修正 | 汪佳凯 | 2026-03-03 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46077% | 操作異常 | 任務異常 16 天
41.1 | M251201R1 | 緊湊型渦街流量計導入專案 | 產品規格比較一覽表 (ISO表單：QR-C-22) | 陳奕宏 | 2026-02-25 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46077% | 操作異常 | 任務異常 22 天
41.2 | M251201R1 | 緊湊型渦街流量計導入專案 | 新產品成果內部產品 & 技術說明會 | 陳奕宏 | 2026-02-25 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46077% | 操作異常 | 任務異常 22 天
41.3 | M240101P1 | 首次生產-液體洩漏偵測器 | 設變 | 黃胤綸 | 2026-03-03 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46078% | 操作異常 | 任務異常 16 天
41.4 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 文件審查 (BOM.圖面.SOP) | 鄭華瑜 | 2026-03-03 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46078% | 操作異常 | 任務異常 16 天
41.5 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 開立內聯單請生管進行PCBA打件 (基本：A:20套 / K:50套 / M:100套，需在專案會議再次確認) | 周家儀 | 2026-03-31 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46079% | 操作異常
41.6 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | DVT-QA樣機EOM建立 | 王瀚霆 | 2026-03-02 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46079% | 操作異常 | 任務異常 17 天
41.7 | M251201R1 | 緊湊型渦街流量計導入專案 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 陳奕宏 | 2026-02-26 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46079% | 操作異常 | 任務異常 21 天
41.8 | K231101P1 | 首次生產-AI伺服器用熱質流量計 | MP發行 | 余依錚 | 2026-03-06 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46083% | 操作異常 | 任務異常 13 天
41.9 | D260102R1 | 2026年程式碼審查1st | EPU2 | 張政崙 | 2026-03-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46084% | 操作異常 | 任務異常 10 天
42 | D260103R1 | HART dd先期研究案 | HART dd file開發環境工具架設 | 蕭金椿 | 2026-03-30 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46084% | 操作異常
42.1 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | SOP修正 | 蘇漢城 | 2026-03-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46084% | 操作異常 | 任務異常 10 天
42.2 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | DVT-QA測試(CNPA49第4版) | 朱哲演 | 2026-03-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46084% | 操作異常
42.3 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 型錄、DM與操作手冊草稿編修檔資料 (發起PLM提供給FAE) | 何昆達 | 2026-03-05 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46084% | 操作異常 | 任務異常 14 天
42.4 | M240101P1 | 首次生產-液體洩漏偵測器 | SOP修正 | 蘇漢城 | 2026-03-10 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46085% | 操作異常 | 任務異常 9 天
42.5 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | PVT技轉會議紀錄 | 王淑瑤 | 2026-03-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46085% | 操作異常 | 任務異常 10 天
42.6 | M240803P1 | EGX5防腐型技转 | 結案會議紀錄 | 汪佳凯 | 2026-03-04 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46085% | 操作異常 | 任務異常 15 天
42.7 | M251201C1 | GPX 申請UL-61010認證 | GPX 溫升測試、拉力測試、過載測試、IP測試......等 | 賴慶樺 | 2026-03-24 | #VALUE! | #VALUE! | 2026-02-12 |  |  | Complete | 0 | 2026/02/09 | 46085%
42.8 | M240803P1 | EGX5防腐型技转 | 結案報告 | 汪佳凯 | 2026-03-18 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46086% | 操作異常 | 任務異常 1 天
42.9 | D260102R1 | 2026年程式碼審查1st | EPV | 張文魁 | 2026-03-16 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46091% | 操作異常 | 任務異常 3 天
43 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 結案會議紀錄 | 蘇漢城 | 2026-03-10 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46091% | 操作異常 | 任務異常 9 天
43.1 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 開立工單(工單、預計生產時間) | 周家儀 | 2026-03-12 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46091% | 操作異常 | 任務異常 7 天
43.2 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 結案報告 | 蘇漢城 | 2026-03-24 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46092% | 操作異常
43.3 | M240101P1 | 首次生產-液體洩漏偵測器 | 結案會議紀錄 | 蘇漢城 | 2026-03-11 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46092% | 操作異常 | 任務異常 8 天
43.4 | M240101P1 | 首次生產-液體洩漏偵測器 | 結案報告 | 蘇漢城 | 2026-03-25 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46093% | 操作異常
43.5 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 缺料採購(採購單) | 曾瑞琳 | 2026-03-26 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46094% | 操作異常
43.6 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 開立內聯單請廠務進行PCBA打件 (基本：A:20套 / K:50套 / M:100套，需在專案會議再次確認) | 許博元 | 2026-03-16 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 0 | 46097% | 操作異常 | 任務異常 3 天
43.7 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 測試治具設計及製作/移交清單 | 陳威諭 | 2026-04-07 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
43.8 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | QC工程表 | 許博元 | 2026-03-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
43.9 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 進料檢驗基準 | 許博元 | 2026-03-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
44 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 產品檢驗基準 | 許博元 | 2026-03-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
44.1 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 產品檢驗記錄 | 許博元 | 2026-03-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
44.2 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 成品 EBOM(含零件庫存清單、採購建議書) | 許博元 | 2026-03-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
44.3 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 機構圖面 | 葉宏政 | 2026-03-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46097% | 操作異常
44.4 | D260102R1 | 2026年程式碼審查1st | SBX | 李奕澔 | 2026-03-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46098% | 操作異常
44.5 | K251101R1 | 精巧型電磁流量計 | 樣品系統驗證,測試及問題解決(軟體/硬體/機構整合) | 魏暉恩 | 2026-04-17 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46100% | 操作異常
44.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
44.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
44.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
44.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
45.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
46.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
47.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
47.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
47.3 | M240803P1 | EGX5防腐型技转 | 結案文件審查 | 汪佳凯 | 2026-03-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46100% | 操作異常
47.4 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | SOP/加工重點 (半成品/成品/組裝/測試) | 許博元 | 2026-04-07 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46104% | 操作異常
47.5 | D260102R1 | 2026年程式碼審查1st | SBX2 | 李奕澔 | 2026-03-30 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
47.6 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | CNPA49第4版型式認證送測(DN13~DN50)各5只 | 何昆達 | 2026-05-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
47.7 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | DVT-QA測試報告簽核 | 朱哲演 | 2026-03-26 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
47.8 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 測試治具設計及製作/移交清單 | 蘇漢城 | 2026-05-07 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
47.9 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | EPH2QC工程表 | 洪子芸 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
48 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 新零件進料檢驗基準 | 洪子芸 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
48.1 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | EPH2產品檢驗記錄 | 洪子芸 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
48.2 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | EPH2-SOP/加工重點 (半成品/成品/組裝/測試) | 洪子芸 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
48.3 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | EPH2產品檢驗基準 | 洪子芸 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
48.4 | M240803P1 | EGX5防腐型技转 | MP發行 | 汪佳凯 | 2026-03-26 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46105% | 操作異常
48.5 | M251201C1 | GPX 申請UL-61010認證 | GPX測試報告草稿，確認其內容描述正確惍 | 賴慶樺 | 2026-03-30 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/02/11 | 46105% | 操作異常
48.6 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | 結案文件審查 | 蘇漢城 | 2026-03-27 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46106% | 操作異常
48.7 | M240101P1 | 首次生產-液體洩漏偵測器 | 結案文件審查 | 余依錚 | 2026-03-30 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46107% | 操作異常
48.8 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 品質檢驗(檢驗紀錄、基準) | 杜至 | 2026-04-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46108% | 操作異常
48.9 | D250301R1 | EPD電磁流量計技转 | 設變 | 汪佳凯 | 2026-04-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46111% | 操作異常
49 | K201002P2 | (K201002R2)SP數位熱質式開關-DC一體型II | MP發行 | 蘇漢城 | 2026-04-01 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46111% | 操作異常
49.1 | M251201C1 | GPX 申請UL-61010認證 | 證書上傳BPM | 賴慶樺 | 2026-03-30 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46111% | 操作異常
49.2 | D260102R1 | 2026年程式碼審查1st | SC38 | 張政崙 | 2026-04-08 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46112% | 操作異常
49.3 | D260103R1 | HART dd先期研究案 | HART dd file製作 | 蕭金椿 | 2026-05-14 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46112% | 操作異常
49.4 | M240101P1 | 首次生產-液體洩漏偵測器 | MP發行 | 余依錚 | 2026-04-02 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46112% | 操作異常
49.5 | D260102R1 | 2026年程式碼審查1st | SC2428 | 李奕澔 | 2026-04-15 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46121% | 操作異常
49.6 | D250301R1 | EPD電磁流量計技转 | SOP修正 | 汪佳凯 | 2026-04-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46122% | 操作異常
49.7 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 首次生產(生產管制表) | 蘇漢城 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46122% | 操作異常
49.8 | M251001R1 | SDX緊湊型光電開關設計 | 產品規格比較一覽表 (ISO表單：QR-C-22) | 彭志豪 | 2026-04-10 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46122% | 操作異常
49.9 | M251001R1 | SDX緊湊型光電開關設計 | 新產品成果內部產品 & 技術說明會 | 彭志豪 | 2026-04-14 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46126% | 操作異常
50 | M251001R1 | SDX緊湊型光電開關設計 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 彭志豪 | 2026-04-17 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46126% | 操作異常
50.1 | D260102R1 | 2026年程式碼審查1st | SE29 | 蕭金椿 | 2026-04-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46128% | 操作異常
50.2 | K251101R1 | 精巧型電磁流量計 | DVT-QA樣機EOM建立 | 魏暉恩 | 2026-04-20 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46132% | 操作異常
50.3 | D250301R1 | EPD電磁流量計技转 | 結案文件審查 | 汪佳凯 | 2026-04-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46133% | 操作異常
50.4 | K251101R1 | 精巧型電磁流量計 | 型錄、DM與操作手冊草稿編修檔資料 (發起PLM提供給FAE) | 魏暉恩 | 2026-04-23 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46133% | 操作異常
50.5 | D260102R1 | 2026年程式碼審查1st | SPX2 | 蕭金椿 | 2026-04-29 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/02/13 | 46135% | 操作異常
50.6 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | PCB 圖面 | 許慧芝 | 2026-05-05 | #VALUE! | #VALUE! |  |  |  | Active | 0 | 2026/01/21 | 46135% | 操作異常
50.7 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 產品規格比較一覽表 (ISO表單：QR-C-22) | 何昆達 | 2026-05-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46135% | 操作異常
50.8 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | PVT-QA測試驗證 | 王琇眉 | 2026-06-04 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46135% | 操作異常
50.9 | D250301R1 | EPD電磁流量計技转 | MP發行 | 汪佳凯 | 2026-05-06 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46136% | 操作異常
51 | K251101R1 | 精巧型電磁流量計 | DVT-QA測試(含競爭樣機性能對照) | 王琇眉 | 2026-05-27 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46136% | 操作異常
51.1 | K251101R1 | 精巧型電磁流量計 | 行銷確認首產及送樣規格及套數 | 吳志嘉 | 2026-05-27 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46136% | 操作異常
51.2 | K251101R1 | 精巧型電磁流量計 | 工況試煉送樣(DN25) | 魏暉恩 | 2026-05-08 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46136% | 操作異常
51.3 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 工程試製(RD主導) | 陳威諭 | 2026-06-16 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46142% | 操作異常
51.4 | D260103R1 | HART dd先期研究案 | HART dd file整合測試 | 蕭金椿 | 2026-05-29 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46157% | 操作異常
51.5 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 證書取得並上傳(BPM) | 陳威諭 | 2026-05-29 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46163% | 操作異常
51.6 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 取得防爆認證測試報告 | 陳威諭 | 2026-05-29 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46163% | 操作異常
51.7 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 工程試製與生產良率統計DN13-100只 | 陳義雄 | 2026-05-28 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46164% | 操作異常
51.8 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 工程試製與生產良率統計DN20-500只 | 陳義雄 | 2026-06-04 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46164% | 操作異常
51.9 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 工程試製與生產良率統計DN25-500只 | 陳義雄 | 2026-06-04 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46164% | 操作異常
52 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | EPH2-機構圖面(元件/組裝/銘版) | 王瀚霆 | 2026-06-04 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | #REF! | #REF!
52.1 | K251101R1 | 精巧型電磁流量計 | 開立內聯單請生管進行PCBA打件 (基本：A:20套 / K:50套 / M:100套，需在專案會議再次確認) | 周家儀 | 2026-06-30 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46170% | 操作異常
52.2 | K251101R1 | 精巧型電磁流量計 | 測試治具設計及製作/移交清單 | 魏暉恩 | 2026-07-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46170% | 操作異常
52.3 | K251101R1 | 精巧型電磁流量計 | QC工程表 | 魏暉恩 | 2026-06-03 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46170% | 操作異常
52.4 | K251101R1 | 精巧型電磁流量計 | 進料檢驗基準 (表單QR-B-15) | 魏暉恩 | 2026-06-03 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46170% | 操作異常
52.5 | K251101R1 | 精巧型電磁流量計 | 產品檢驗基準 | 魏暉恩 | 2026-06-03 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46170% | 操作異常
52.6 | K251101R1 | 精巧型電磁流量計 | 產品檢驗記錄 | 魏暉恩 | 2026-06-03 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46170% | 操作異常
52.7 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | OTC送樣承認 | 陳俊儒 | 2026-06-12 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46174% | 操作異常
52.8 | K251101R1 | 精巧型電磁流量計 | SOP/加工重點 (半成品/成品/組裝/測試) | 魏暉恩 | 2026-07-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46177% | 操作異常
52.9 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 工程試製與生產良率統計DN40-100只 | 陳義雄 | 2026-06-11 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46178% | 操作異常
53 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 工程試製與生產良率統計DN50-100只 | 陳義雄 | 2026-06-11 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46178% | 操作異常
53.1 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 設變 | 彭志豪 | 2026-06-11 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46178% | 操作異常
53.2 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 新產品成果內部產品 & 技術說明會 | 王瀚霆 | 2026-06-24 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46185% | 操作異常
53.3 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | SOP修正 | 蘇漢城 | 2026-06-18 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46185% | 操作異常
53.4 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 陳威諭 | 2026-06-17 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46190% | 操作異常
53.5 | M250301C1 | 一體型電磁流量計北美多重防爆認證 | 證書上傳BPM | 陳威諭 | 2026-06-17 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46190% | 操作異常
53.6 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 結案會議紀錄 | 蘇漢城 | 2026-06-22 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46195% | 操作異常
53.7 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 結案報告 | 蘇漢城 | 2026-07-06 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46196% | 操作異常
53.8 | K251001R1 | EPH水量計型式認證技術規範CNPA49第4版結構驗證與改善 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 王瀚霆 | 2026-06-25 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46198% | 操作異常
53.9 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | 結案文件審查 | 余依錚 | 2026-07-09 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46210% | 操作異常
54 | K251101R1 | 精巧型電磁流量計 | 工程試製 or 工況分析報告 | 魏暉恩 | 2026-08-11 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.1 | K251101R1 | 精巧型電磁流量計 | 機構圖面(元件/組裝/銘版) | 葉宏政 | 2026-07-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.2 | K251101R1 | 精巧型電磁流量計 | 成品 EBOM(含零件庫存清單、採購建議書) | 魏暉恩 | 2026-07-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.3 | K251101R1 | 精巧型電磁流量計 | PCB 圖面 | 許慧芝 | 2026-07-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.4 | K251101R1 | 精巧型電磁流量計 | 標籤貼紙 (回覆標籤版型料號) | 魏暉恩 | 2026-07-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.5 | K251101R1 | 精巧型電磁流量計 | 產品規格比較一覽表 (ISO表單：QR-C-22) | 魏暉恩 | 2026-07-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.6 | M240703P1 | 首次生產-SDX光電系列整併與優化案 | MP發行 | 余依錚 | 2026-07-14 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46213% | 操作異常
54.7 | K251101R1 | 精巧型電磁流量計 | 新產品成果內部產品 & 技術說明會 | 魏暉恩 | 2026-08-21 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46246% | 操作異常
54.8 | K251101R1 | 精巧型電磁流量計 | 列印專案繳付清單(簽核)-SmartQ PLM026 | 魏暉恩 | 2026-08-24 | #VALUE! | #VALUE! |  |  |  | Pending | 0 | 0 | 46258% | 操作異常
54.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.1 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.2 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.3 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.4 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.5 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.6 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.7 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.8 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
55.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.1 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.2 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.3 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.4 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.5 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.6 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.7 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.8 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
56.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.1 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.2 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.3 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.4 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.5 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.6 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.7 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.8 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
57.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.1 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.2 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.3 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.4 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.5 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.6 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.7 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.8 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
58.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.1 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.2 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.3 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.4 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.5 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.6 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.7 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.8 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
59.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.1 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.2 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.3 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.4 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.5 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.6 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.7 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.8 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
60.9 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
61 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! |  |  |  | 0 | 0 | 0 | 0%
61.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
61.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
62.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
63.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
64.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
65.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
66.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
67.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
68.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
69.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
70.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
71.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
72.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
73.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
74.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
75.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
76.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
77.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
78.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
79.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
80.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
81.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
82.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
83.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
84.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
85.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
86.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
87.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
88.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
89.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
90.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
91.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
92.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
93.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
94.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
95.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
96.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
97.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
98.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
99.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
100.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
101.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
102.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
103.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
104.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
105.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
106.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
107.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
108.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
109.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
110.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
111.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
112.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
113.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
114.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
115.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
116.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
117.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
118.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
119.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
120.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
121.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
122.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
123.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
124.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
125.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
126.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
127.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
128.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
129.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
130.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
131.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
132.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
133.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
134.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
135.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
136.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
137.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
138.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
139.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
140.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
141.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
142.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
143.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
144.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
145.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
146.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
147.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
148.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
149.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
150.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
151.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
152.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
153.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
154.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
155.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
156.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
157.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
158.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
159.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
160.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
161.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
162.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
163.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
164.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
165.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
166.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
167.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
168.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
169.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
170.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
171.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
172.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
173.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
174.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
175.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
176.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
177.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
178.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
179.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
180.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
181.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
182.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
183.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
184.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
185.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
186.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
187.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
188.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
189.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
190.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
191.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
192.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
193.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
194.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
195.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
196.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
197.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
198.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
199.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
200.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
201.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
202.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
203.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
204.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
205.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
206.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
207.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
208.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
209.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
210.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
211.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
212.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
213.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
214.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
215.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
216.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
217.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
218.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
219.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
220.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
221.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
222.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
223.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
224.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
225.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
226.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
227.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
228.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
229.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
230.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
231.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
232.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
233.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
234.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
235.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
236.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
237.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
238.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
239.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
240.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
241.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
242.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
243.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
244.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
245.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
246.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
247.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
248.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
249.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
250.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
251.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
252.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
253.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
254.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
255.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
256.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
257.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
258.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
259.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
260.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
261.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
262.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
263.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
264.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
265.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
266.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
267.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
268.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
269.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
270.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
271.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
272.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
273.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
274.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
275.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
276.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
277.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
278.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
279.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
280.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
281.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
282.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
283.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
284.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
285.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
286.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
287.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
288.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
289.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
290.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
291.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
292.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
293.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
294.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
295.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
296.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
297.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
298.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
299.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
300.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
301.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
302.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
303.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
304.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
305.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
306.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
307.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
308.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
309.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
310.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
311.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
312.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
313.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
314.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
315.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
316.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
317.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
318.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
319.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
320.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
321.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
322.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
323.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
324.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
325.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
326.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
327.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
328.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
329.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
330.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
331.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
332.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
333.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
334.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
335.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
336.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
337.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
338.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
339.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
340.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
341.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
342.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
343.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
344.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
345.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
346.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
347.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
348.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
349.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
350.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
351.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
352.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
353.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
354.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
355.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
356.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
357.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
358.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
359.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
360.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
361.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
362.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
363.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
364.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
365.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
366.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
367.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
368.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
369.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
370.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
371.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
372.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
373.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
374.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
375.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
376.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
377.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
378.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
379.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
380.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
381.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
382.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
383.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
384.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
385.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
386.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
387.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
388.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
389.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
390.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
391.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
392.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
393.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
394.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
395.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
396.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
397.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
398.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
399.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
400.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
401.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
402.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
403.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
404.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
405.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
406.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
407.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
408.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
409.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
410.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
411.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
412.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
413.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
414.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
415.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
416.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
417.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
418.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
419.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
420.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
421.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
422.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
423.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
424.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
425.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
426.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
427.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
428.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
429.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
430.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
431.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
432.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
433.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
434.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
435.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
436.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
437.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
438.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
439.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
440.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
441.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
442.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
443.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
444.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
445.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
446.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
447.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
448.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
449.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
450.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
451.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
452.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
453.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
454.7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!